Oregon SIP Workplan:

Project Title: Oregon Nurses on Strategic Healthcare Boards

Project Director: TBD

Area of Focus: IOM Recommendation #7 - Prepare and enable nurses to lead change to advance health

Project Goal: Oregon will have 200 nurses serving as public, private, and governmental healthcare decision makers on strategic, key healthcare boards.

| Objectives | Action Steps | Target Date | Responsible Person | Deliverables |
| --- | --- | --- | --- | --- |
|  |  |  |  | 18-Month | 24-Month |

| 1. Identify strategic positions, key decision-making and influential healthcare boards for transforming healthcare, and identify nurses currently serving on boards. | Generate a list of healthcare boards in Oregon and current nurse membership, including: Nursing boards Community Care Organization (CCO) boards Acute care hospital/health system boards Legislative bodies for relevant committee placements Federally Qualified Health Centers | 3/1/16 | Project Director OAC Volunteer: Tom Engle | List of healthcare boards as described | Updated list |
| --- | --- | --- | --- | --- | --- |
|  | Analyze Oregon healthcare boards and determine the most influential healthcare decision making boards in Oregon - areas of greatest need for new models of care (e.g. rural regions) or boards with great influence on emerging models of care (CCOs) | 4/15/16 | Project Director OAC Volunteer: TBD | Prioritized listing of influential boards | Re-evaluated as needed, on-going |
|  | Coordinate information gathered with Nurses On Boards Coalition | 4/1/16 and on-going | Project Director OACV: Jake Creviston | Content coordinate with the NOBC |  |
|  | Create contact list for targeted boards. | 5/1/16 | Project Director | Contact List Created | Updated list |
|  | Using list of targeted boards, identify any nurses currently serving on those boards | 6/1/16 | Project Director | Contact List Created | Updated List |
|  | Using website and other communication methods, encourage nurses to self-identify their board service by participating in national NOBC data collection process | 5/1/16 | Project Director | Communication strategy created and implemented | Ongoing communication |
|  | Coordinate with National NOBC movement to identify nurses serving on Boards in Oregon on an ongoing basis | 9/1/16 | Project Director | Process for receiving data identified |  |

| Objectives | Action Steps | Target Date | Responsible Person | Deliverables |
| --- | --- | --- | --- | --- |
|  |  |  |  | 18-Month | 24-Month |
| 2. Increase the number of nurses prepared for leadership roles in healthcare policy, design, and decision-making on healthcare boards. | Develop roster of nurses available for/interested in board service: Set criteria for identification; Utilize Steering Committee members and identified nurse trustees to identify potential board candidates Set categories for recruitment based on diversity, readiness, board interest, and preparation need and level. To ensure inclusivity, reach out to professional nursing organizations such as the National Association of Hispanic Nurses and the Asian American/Pacific Islander Nurses Association to identify nurse leaders from diverse backgrounds. | 2/1/16 3/1316 4/1/16 | Project Director OACV: Leslie Ray and Jana Bitton | Create categorized roster based on recruitment efforts | Updated roster |
|  | Identify resources related to recruiting nurses on boards and if necessary, create a set of resource materials (toolkit), including currently existing resources, for nurses to further their move to board and policy positions, e.g.: Mentor roster Brochures Quick facts guide to board service w/links Podcasts through the OCN NurseCast series Readiness assessment | 7/1/16 | Project Director OACV: Renee Menkens | Board service toolkit initiated and includes: Value brochure created “How To” for state agencies Readiness assessment Dedicated web page/s for board service tools and resources | Board Service toolkit completed and includes: Video guide Planning Your Path to the Boardroom Podcasts |
|  | Identify existing board/mentor training programs. Adopt existing resources or create new if necessary to implement local training. | 3/13/16 | Project Director OACV: Renee Menkens, Jake Creviston, Iris Boston | Two existing programs identified | Local training implemented by OAC and partners |
|  | Convene a group of nurse and other healthcare trustees to identify strategies for board appointments Include nurses from diverse backgrounds where appropriate. | 3/1/16 | Project Director Jana Bitton | Strategies incorporated into resource materials |  |
|  | Promote board training programs to Oregon nurses | 4/1/16 | Project Director OACV: Renee Menkens, Jake Creviston | 10 nurses have participated in board training | 25 nurses have participated in board training |
| 3. Increase awareness among nurses, other health professionals, and key healthcare decision-makers of the value of nurse board service | Develop relationships with leaders of identified strategic boards, decision-making organizations, and influential positions to engage them in the IOM recommendations and the value nursing’s contribution to their decision-making process. Specifically identify and reach out to leaders of professional groups that support diverse populations. | 3/1/16 | Jake Creviston and Renee Menkens | Establish 6 strategic relation-ships with leaders from boards identified from Objective #1 | Establish a total of 12 strategic relation-ships with leaders from boards identified from Objective #1 |
|  | Utilize the national Nurses on Boards campaign through the Campaign for Action and the Oregon Action Coalition Communications Workgroup to develop or modify materials to share with board leaders. | 12/1/15 and on-going | Jake Creviston, Jennifer Feeney & Tamara Rose | Materials identified and into resources |  |
|  | Raise awareness of the importance of nurses on boards through social media, blogs, and OCN’s Oregon NurseCast podcast | 12/1/15 and on-going | Project Director OACV: Jake Creviston & Jana Bitton | 3 podcasts created for marketing & education (see Project Goal #2 above) | 6 podcasts |
|  | Share information through presentations across the state about the need to diversify hospital/health system/health policy boards | 6/1/16 | Project Director, Jake Creviston, Iris Boston | 2 presenta-tions given | 6 presenta-tions given |
|  | Seek out and engage other health professionals in attempt to develop nursing’s multidisciplinary approach to healthcare and board service Engage a diverse group of health professionals, specifically reaching out to students, health professionals in rural areas, professionals of under-represented race, gender, ethnicity, etc. | 12/1/15 and on-going | Project Director, Jake Creviston | 20 health profession organiza-tions in Oregon contacted |  |
|  | Hold a summit on nursing leadership on healthcare boards to achieve the Triple Aim and move to a culture of health This summit will be a one-day program featuring keynote presentations and breakout sessions with panelists or additional speakers. Topics will range from best practices for recruiting nurses to boards, success stories from nurses on boards in Oregon and nationwide, and emphasis on the need for nurses to seek out opportunities to share their knowledge, the need for board members who make decisions on health policy to seek out the voice of nurses, and cultural competency training. Time will also be allocated for networking to allow nurses from the program who are now prepared to serve on boards to connect with potential board leaders. The audience will be about 100 – 150 people. Attendees will be nurses who have participated in the training programs, leaders from identified boards, community members and nurses who have an interest in the topic, and legislators who support health transformation in Oregon. To increase the diversity of the meeting, a stipend will be provided for participants to travel from rural areas of the state to attend the summit. | 4/1/17 | Project Director, ONSHB Team | Summit Held |  |
|  | The project will be staffed by a .5 FTE project coordinator and the executive director of the Oregon Center for Nursing (OCN) will serve as principal investigator. Hire project coordinator (PC) to build the infrastructure needed to support the OAC and accomplish the objectives of the Nurses on Strategic Health/Healthcare Boards project. Project coordinator and OCN executive director will be responsible for: Develop a strategic plan with action steps for implementation Communicate outcomes to the community Identify new volunteers and partners to sustain the project Create a plan for sustainability beyond the grant program | January 2016 3/1/2016 Ongoing Ongoing June 2017 | Jana Bitton (PI) PC PC PI PI | Project coordinator hired Strategic plan created Website created 5 new volunteers identified | Strategic plan reviewed Website updated 8 total volunteer identified Sustainability plan created |