Oregon SIP Workplan:

Project Title: Oregon Nurses on Strategic Healthcare Boards

Project Director: [Name]

Area of Focus: IOM Recommendation #7 - Prepare and enable nurses to lead change to advance health

Project Goal: Increase the number of nurses serving as public, private, and governmental healthcare decision makers on strategic, key healthcare boards.

| Objectives | Action Steps | Target Date | Responsible Person | Deliverables |
| --- | --- | --- | --- | --- |
|  |  |  |  | 18-Month | 24-Month |

| 1. Identify strategic positions, key decision-making and influential healthcare boards for transforming healthcare | Generate a list of healthcare boards in Oregon and current nurse membership, including: Nursing boards (e.g., Oregon Nurses Association, Oregon Center for Nursing, Oregon State Board of Nursing) Community Care Organization (CCO) boards (Cascade Health Alliance, Eastern Oregon, Trillium Community, etc.) Acute care hospital/health system boards (Legacy Health System, Grand Ronde Hospital, Sky Lakes Medical Center, etc.) Federally Qualified Health Centers (e.g., Umpqua Health Center) | 12/1/15 1/1/16 2/1/16 3/1/16 | TE | Updated list | Updated list |
| --- | --- | --- | --- | --- | --- |
|  | Analyze Oregon healthcare boards and determine the most influential healthcare decision making boards in Oregon - areas of greatest need for new models of care (e.g. rural regions) or boards with great influence on emerging models of care (CCOs) | 4/15/16 | LR | Prioritized listing of influential boards | Re-evaluated as needed, on-going |
|  | Coordinate information gathered with Nurses On Boards Coalition | 4/1/16 and on-going | JC |  |  |
|  | Create contact list for targeted boards. | 5/1/16/ | LR | Updated List | Updated list |

| Objectives | Action Steps | Target Date | Responsible Person | Deliverables |
| --- | --- | --- | --- | --- |
|  |  |  |  | 18-Month | 24-Month |
| 2. Increase the number of nurses prepared for leadership roles in healthcare policy, design, and decision-making on healthcare boards. | Develop roster of nurses available for/interested in board service Set criteria for identification; Utilize Steering Committee members and identified nurse trustees to identify potential board candidates Set categories for recruitment based on diversity, readiness, board interest, and preparation need and level | 2/1/16 3/1316 4/1/16 | LR & JB | Updated roster based on recruitment efforts | Updated roster |
|  | Create a set of resource materials (toolkit), including currently existing resources, for nurses to further their move to board and policy positions, e.g.: Mentor roster Brochures Quick facts guide to board service w/links Podcasts through the OCN NurseCast series Readiness assessment | 7/1/16 | RM, PSU 509 Intern | Value brochure created “How To” for state agencies 3 podcasts Readiness assessment Dedicated web page/s for board service tools and resources | Video guide “Planning Your Path to the Boardroom” 6 podcasts |
|  | Identify existing board/mentor training programs (or create new) to implement locally | 3/13/16 | RM, JC, Iris Boston (IB), PSU 509 Intern | 2 existing programs identified | Local training developed by OAC and partners |
|  | Convene a group of nurse and other healthcare trustees to identify strategies for board appointments | 3/1/16 | JB, LR | Strategies incorporated into resource materials |  |
|  | Promote board training programs to Oregon nurses | 4/1/16 | RM, JC, LR | 10 nurses have participated in board training | 25 nurses have participated in board training |

| Objectives | Action Steps | Target Date | Responsible Person | Deliverables |
| --- | --- | --- | --- | --- |
|  |  |  |  | 18-Month | 24-Month |
| 3. Increase awareness among nurses, other health professionals, and key healthcare decision-makers of the value of nurse board service | Develop relationships with leaders of identified strategic boards, decision-making organizations, and influential positions to engage them in the IOM recommendations and the value nursing’s contribution to their decision-making process. | 3/1/16 | JC & LR | 6 strategic relationships established | 12 strategic relationships established |
|  | Utilize the national Nurses on Boards campaign through the Campaign for Action and the Oregon Action Coalition Communications Workgroup to develop or modify materials to share with board leaders. | 12/1/15 and on-going | JC, JF & TR | Materials identified and incorporated into resources |  |
|  | Raise awareness of the importance of nurses on boards through social media, blogs, and OCN’s Oregon NurseCast podcast | 12/1/15 and on-going | JC & JB | 3 podcasts created for marketing & education (see Project Goal #2 above) | 6 podcasts |
|  | Share information through presentations across the state about the need to diversify hospital/health system/health policy boards | 6/1/16 | JC & IB | 2 presentations given | 6 presentations given |
|  | Seek out and engage other health professionals in attempt to develop nursing’s multidisciplinary approach to healthcare and board service | 12/1/15 and on-going | JC | All health professional organizations in Oregon contacted |  |
|  | Conduct a summit on nursing leadership on healthcare boards to achieve the Triple Aim and move a culture of health | 4/1/17 | TE, RM | Summit Held |  |
|  | Hire staff at the Oregon Center for Nursing to build the infrastructure needed to support the OAC and accomplish the objectives of the Nurses on Strategic Health/Healthcare Boards project. | 1/1/16 | JB |  |  |